## Sheet1
Sprint Number | Sprint Duration | Tasks/User Stories Included | Sprint Goals
Sprint 1 | 2 Weeks | US1, US2 | Develop login and password reset
Sprint 2 | 2 Weeks | US3, US4 | Implement account balance and history
Sprint 3 | 2 Weeks | US5 | Enable fund transfer functionality